## Milestones
Area | Number | Task | Due Date | Owner | Status
Preparation | 1 | Topic Approval by Prof. Ledon | 2022-04-27 | AN | DONE
Preparation | 3 | Collect Economic Data Series | 2022-04-28 | AN | DONE
Preparation | 2 | Collect FOMC statements | 2022-05-04 | PT | ACTIVE
Preparation | 4 | Agree Delivery Date and Presentation Date | 2022-05-04 | BOTH | ACTIVE
Data Wrangling | 1 | FOMC statements are staged in pandas dataframe | 2022-05-05 | PT | ACTIVE
Preparation | 5 | Learn LDA Model Usage for FOMC | 2022-05-07 | AN | ACTIVE
Preparation | 6 | Learn Sentiment Analysis Usage for FOMC | 2022-05-07 | PT
Data Wrangling | 2 | Time Series Data is cleansed and returns or changes are derived. | 2022-05-08 | BOTH
Data Wrangling | 3 | Statistical Summaries of FOMC statements: Word Clouds, Chairmanship | 2022-05-08 | AN
Data Wrangling | 4 | Visualization of Financial and Economic Time Series | 2022-05-08 | AN
Data Wrangling | 5 | Preprocess the Text for LDA | 2022-05-08 | AN
Data Wrangling | 6 | Preprocess the Text for Sentiment | 2022-05-08 | PT
Preparation | 7 | Choose Python Packages for LDA Models | 2022-05-08 | AN
Preparation | 8 | Choose Python Packages for Sentiment Models | 2022-05-08 | PT
Preparation | 9 | Choose Sentiment Dictionary for FOMC | 2022-05-08 | PT
Model Building and Comparison | 1 | Run LDA Model | 2022-05-10 | AN
Model Building and Comparison | 3 | Run sentiment index | 2022-05-10 | PT
Preparation | 10 | Choose Python regression and visualization package | 2022-05-10 | BOTH
Discussion and Exposition | 1 | Outline Paper Sections | 2022-05-13 | AN
Model Building and Comparison | 2 | Diagnostics for LDA Topic Model | 2022-05-13 | AN
Model Building and Comparison | 4 | Time Series regression of Sentiment vs. Markets | 2022-05-13 | BOTH
Discussion and Exposition | 2 | Discuss LDA: Connect topic weights to real world policy making. | 2022-05-15 | AN
Discussion and Exposition | 3 | Discuss Sentiment: | 2022-05-15 | PT
Discussion and Exposition | 4 | Background literature | 2022-05-15 | AN
Discussion and Exposition | 5 | Executive summary + conclusions. | 2022-05-15 | BOTH
Discussion and Exposition | 6 | Final Draft comments integrated | 2022-05-16 | BOTH
Presentation | 1 | Choose Presentation Software | 2022-05-17 | BOTH
Presentation | 2 | Circulate draft 1 - presentation slides | 2022-05-18 | BOTH
Presentation | 3 | Discuss + update talking points | 2022-05-19 | BOTH
Presentation | 4 | Upload video | 2022-05-20 | AN
Wrap Up | 1 | Everything uploaded to Github with proper naming | 2022-05-20 | BOTH
Wrap Up | 2 | We can run all code individually. | 2022-05-21 | BOTH
Wrap Up | 3 | Videos links and Github links are resume ready | 2022-05-21 | BOTH
Wrap Up | 4 | Submit Project in Blackboard | 2022-05-22 | BOTH

## FOMC 2019-2022
Year | Date | Target Rate Decision | Is Ordinary Meeting | Include in Study | Note | Rate Range
2019 | 2019-01-30 | No change | Yes | Yes |  | 2.25-2.5
2019 | 2019-03-20 | No change | Yes | Yes
2019 | 2019-05-01 | No change | Yes | Yes
2019 | 2019-06-19 | No change | Yes | Yes
2019 | 2019-07-31 | Decrease | Yes | Yes |  | 2.00-2.25
2019 | 2019-09-18 | Decrease | Yes | Yes |  | 1.75-2.00
2019 | 2019-10-04 | No change | No | No | Purchase of T-Bills and Repo purchases and reinvestment of Principal
2019 | 2019-10-30 | Decrease | Yes | Yes |  | 1.50-1.75
2019 | 2019-12-11 | No change | Yes | Yes
2020 | 2020-01-29 | No change | Yes | Yes | No mention of Covid
2020 | 2020-03-03 | Decrease | No | Yes | First mention of Coronavirus | 1.00-1.25
2020 | 2020-03-15 | Decrease | No | Yes | More coronavirus support. Low inflation expectations. Support other central bank with US dollar swap lines. | 0.00-0.25
2020 | 2020-03-19 | No change | No | No | notation vote to expand swap lines with more central banks.
2020 | 2020-03-23 | No change | No | No | Begin purchase of Agency CMBS
2020 | 2020-03-31 | No change | No | No | Establish temporary FIMA repo facility to support central banks.
2020 | 2020-04-29 | No change | Yes | Yes | Coronavirus is slowing the economy and credit
2020 | 2020-06-10 | No change | Yes | Yes | Ongoing public health crisis..
2020 | 2020-07-29 | No change | Yes | Yes | Overall financial conditions have improved . Coronavirus is key issue.
2020 | 2020-08-27 | No change | No | No | Longer-Run Goals and Monetary Policy Framework
2020 | 2020-09-16 | No change | Yes | Yes | Exclude lengthy addendum on Monetary Policy Implementation in PDF version.
2020 | 2020-11-05 | No change | Yes | Yes | Recovery from Covid. Inflation still low. Unemployment still bad.
2020 | 2020-12-16 | No change | Yes | Yes | Recovery from Covid continues. Gives specific asset purchases volumes targets.
2021 | 2021-01-27 | No change | Yes | Yes | Recovery from Covid has slowed. Inflation is low. Employment recovering.
2021 | 2021-03-17 | No change | Yes | Yes | Covid still bad. Recovery slowed but sped up. Inflation still low. Asset purchases continue.
2021 | 2021-04-28 | No change | Yes | Yes | Vaccinations helping to reduce Covid. Some sectors are weak but recovering. Inflation has risen. Economy recovering.
2021 | 2021-06-16 | No change | Yes | Yes | Vaccinations reducing Covid. Inflation has risen but transitory. Asset purchases will continue.
2021 | 2021-07-28 | No change | Yes | Yes | Inflation has risen but transitory.
2021 | 2021-09-22 | No change | Yes | Yes | Inflation is elevated but transitory. Asset purchases may slow in future.
2021 | 2021-11-03 | No change | Yes | Yes | Inflation is elevated but expected to be transitory. economy and employment continue to strengthen. Asset purchases will begin to slow.
2021 | 2021-12-15 | No change | Yes | Yes | continued elevated inflation. vaccinations controlling coronavirus. Asset purchases will slow. | 0.00-0.25
2022 | 2022-01-26 | No change | Yes | Yes | Inflation well above 2 percent and strong labor market, hints at future rate hikes. Asset purchases will slow. | 0.00-0.25
2022 | 2022-03-16 | Increase | Yes | Yes | Unemployment rate declined. Ukraine invasion will increase inflation pressure. Asset sales hinted in future meetings. | 0.25-0.50
2022 | 2022-05-04